## Slide 1
WORKSTREAM / OWNER | WEEKS 1–2 Approve & baseline | WEEKS 3–4 Build & test | WEEKS 5–8 Pilot & learn | WEEKS 9–12 Prove & decide
Data & access Source steward | Approved corpus Access register | Source refresh Named stewards | Weekly access and freshness checks | Audit closeout Release inventory
Workflow & product Product lead | Task mapping Baseline time logs | Grounded draft Visible citations | 15-user pilot Defect fixes | Release candidate Runbook
Quality & controls Expert reviewer | Risk boundaries Review criteria | Test pack Rejection reasons | 10 reviewed tasks Error triage | 20 completed tasks Gate evidence
Adoption & value Practice lead | Sponsor & users Agree tracking | Training & support Measurement plan | Weekly usage Feedback sessions | Benefit case Scale recommendation
Run the pilot through four evidence gates
Owners run the workstreams. Evidence gates release the next phase.
EVIDENCE GATES
G1 · Week 2
Corpus + access signed
G2 · Week 4
Test pack approved
G3 · Week 8
10 tasks reviewed
G4 · Week 12
Practice lead + CFO
decide
DEPENDENCIES
Permissions before retrieval tests
Approved test pack before pilot
Quality evidence before benefit case
STOP RULE
No expansion while critical data exceptions remain open.
Notes: Each pilot engagement supplies one research task. Twenty paired tasks correspond to twenty engagements. The practice lead and CFO release scale funding only after the evidence gates are reviewed. Critical data exceptions stop expansion. [SlidePoise sources] Generated target visual: /Users/henry/Codes/AI_slide_drafting/examples/consulting-ai-transformation/run/slides/s04-delivery-roadmap/work/accepted-slide.png Canonical asset remix-flag-line: /Users/henry/Codes/AI_slide_drafting/examples/consulting-ai-transformation/run/work/icon-cache/flag/remix-flag-line.svg