## Slide 1
WORKSTREAM / OWNER | WEEKS 1–2 Approve & baseline | WEEKS 3–4 Build & test | WEEKS 5–8 Pilot & learn | WEEKS 9–12 Prove & decide
Data & access Source steward | Approved corpus Access register | Source refresh Named stewards | Weekly access and freshness checks | Audit closeout Release inventory
Workflow & product Product lead | Task mapping Baseline time logs | Grounded draft Visible citations | 15-user pilot Defect fixes | Release candidate Runbook
Quality & controls Expert reviewer | Risk boundaries Review criteria | Test pack Rejection reasons | 10 reviewed tasks Error triage | 20 completed tasks Gate evidence
Adoption & value Practice lead | Sponsor & users Agree tracking | Training & support Measurement plan | Weekly usage Feedback sessions | Benefit case Scale recommendation
Run the pilot through four evidence gates
Owners run the workstreams. Evidence gates release the next phase.
EVIDENCE GATES
G1
Week 2
Corpus +
access
signed
G2
Week 4
Test pack
approved
G3
Week 8
10 tasks
reviewed
G4
Week 12
Practice
lead + CFO
decide
DEPENDENCIES
Permissions before retrieval tests
Approved test pack before pilot
Quality evidence before benefit case
STOP RULE
No expansion while critical data exceptions remain open.
Notes: [SlidePoise sources] Generated target visual: /Users/henry/Codes/AI_slide_drafting/output/showcase-revisions/consulting-v3-authoring/slides/s04-delivery-roadmap/work/accepted-slide.png