## Slide 1
Measure | Minimum to scale
Cycle-time reduction | 25%
Sampled cited claims verified | 95%
Critical data exceptions | 0
Weekly-active pilot users | 70% · at least 11 of 15
Prove the research pilot before scaling AI
One practice. 15 consultants. 20 paired research tasks. A 12-week, $25k pilot.
RESEARCH CAPACITY IMPACT IF WE SCALE
WHY THIS PILOT FIRST
WEEK-12 SCALE GATE
10,800 h
1,944 h
$243k
Annual research baseline
Potential annual capacity
Annual capacity equivalent
900 engagements × 12 h
60% adoption × 30% time reduction
1,944 h × $125 per hour
01
Focus a repeatable task
Approved sources, frequent use
and comparable inputs.
02
Preserve expert review
Verify every client claim
before release.
03
Fund against evidence
Practice lead and CFO release
$60k only after the week-12 gate.
DECISION REQUESTED
Approve $25k and name a practice sponsor.
Notes: All quantities are illustrative planning assumptions. Capacity value is not a cash saving. The 95% gate applies to a sampled test set. Each client release separately requires expert verification and engagement-lead approval. At least 11 of 15 pilot users must be weekly active. One comparable research task is measured per pilot engagement. [SlidePoise sources] Generated target visual: /Users/henry/Codes/AI_slide_drafting/output/showcase-revisions/consulting-v3-authoring/slides/s01-recommendation/work/accepted-slide.png

## Slide 2
Chart: 
| Research synthesis | Proposal drafting | Knowledge retrieval
Illustrative annual capacity hours | 1620 | 1440 | 1080
Workflow | Baseline h | Adoption | Time saved
Research | 12 | 60% | 30%
Proposal | 8 | 50% | 40%
Retrieval | 5 | 60% | 40%
Workflow | Control readiness | Owner | Sequence
Research synthesis | Approved corpus Explicit review | Practice lead | START
Proposal drafting | Claims and commitments need controls | BD lead | NEXT
Knowledge retrieval | Permissions need cleanup | Knowledge lead | LATER
Revise the analysis without rebuilding the slide
Capacity creates the opportunity. Control readiness sets the sequence.
ANNUAL CAPACITY POTENTIAL
PILOT SEQUENCING TEST
WHY RESEARCH WINS FIRST
Illustrative hours
Annual hours = 900 engagements ×
baseline h × adoption × time saved
01
Frequent, comparable tasks
Many engagements use the
same research task.
02
A bounded source corpus
Approved sources limit scope
and simplify review.
03
A named expert reviewer
An accountable reviewer verifies
outputs before client release.
Check task overlap before adding
workflow benefits.
PILOT BOUNDARY
Start with approved-source research synthesis.
Notes: This is an illustrative planning model for fictional Northstar Advisory. Annual capacity assumes 900 engagements. Research uses 900 x 12 baseline hours x 60% adoption x 30% time saved = 1,944 hours. The same formula produces 1,440 proposal hours and 1,080 retrieval hours from the displayed assumptions. The three workflow estimates may overlap and cannot be added without checking task boundaries. Capacity released is not a cash saving. Control readiness determines the proposed sequence, and expert review remains required before any client release. [SlidePoise sources] Generated target visual: /Users/henry/Codes/AI_slide_drafting/output/showcase-revisions/consulting-v3-authoring/slides/s02-opportunities/work/accepted-slide.png

## Slide 3
 | Approved sources | Grounded draft | Expert review | Client-ready output
INPUT | Corpus request | Source pack + task brief | Draft + evidence trail | Signed draft + resolved defects
OUTPUT | Versioned source pack | Cited draft + uncertainty flags | Signed review or defect log | Authorized client deliverable
OWNER | Source steward | Engagement team | Expert reviewer | Engagement lead
RELEASE CONTROL | Verify permissions and dates | Check citations and evidence gaps | Validate claims and quality | Confirm release approval
Keep expert ownership at every release
A controlled path from permissioned evidence to approved client work.
Approved
sources
Grounded
draft
Expert
review
Client-ready
output
Correct sources via exception register
Reject with defect reasons
SHARED CONTROLS
One register records
defects, owners and
disposition.
Platform team maintains
access controls and
audit logs.
PILOT MEASUREMENT
Compare 20 paired
tasks with baseline time
logs.
Verify claim samples
and record expert review
effort.
RELEASE RULE
No client use without expert and engagement-lead sign-off.
Notes: This is an illustrative planning scenario. Twenty paired tasks represent one research task from each of twenty pilot engagements, with ten tasks at the week-eight interim review. The sampled 95% claim-verification gate measures pilot quality. Every client claim still requires expert sign-off and every client release requires engagement-lead approval. The two curved feedback paths are editable native freeforms. They preserve the observed direction and curve geometry, but moving the table or its columns in Office does not automatically reattach these paths. [SlidePoise sources] Generated target visual: /Users/henry/Codes/AI_slide_drafting/output/showcase-revisions/consulting-v3-authoring/slides/s03-operating-model/work/accepted-slide.png

## Slide 4
WORKSTREAM / OWNER | WEEKS 1–2 Approve & baseline | WEEKS 3–4 Build & test | WEEKS 5–8 Pilot & learn | WEEKS 9–12 Prove & decide
Data & access Source steward | Approved corpus Access register | Source refresh Named stewards | Weekly access and freshness checks | Audit closeout Release inventory
Workflow & product Product lead | Task mapping Baseline time logs | Grounded draft Visible citations | 15-user pilot Defect fixes | Release candidate Runbook
Quality & controls Expert reviewer | Risk boundaries Review criteria | Test pack Rejection reasons | 10 reviewed tasks Error triage | 20 completed tasks Gate evidence
Adoption & value Practice lead | Sponsor & users Agree tracking | Training & support Measurement plan | Weekly usage Feedback sessions | Benefit case Scale recommendation
Run the pilot through four evidence gates
Owners run the workstreams. Evidence gates release the next phase.
EVIDENCE GATES
G1
Week 2
Corpus +
access
signed
G2
Week 4
Test pack
approved
G3
Week 8
10 tasks
reviewed
G4
Week 12
Practice
lead + CFO
decide
DEPENDENCIES
Permissions before retrieval tests
Approved test pack before pilot
Quality evidence before benefit case
STOP RULE
No expansion while critical data exceptions remain open.
Notes: Each pilot engagement supplies one research task. Twenty paired tasks correspond to twenty engagements. The practice lead and CFO release scale funding only after the evidence gates are reviewed. Critical data exceptions stop expansion. [SlidePoise sources] Generated target visual: /Users/henry/Codes/AI_slide_drafting/output/showcase-revisions/consulting-v3-authoring/slides/s04-delivery-roadmap/work/accepted-slide.png

## Slide 5
Cost item | Amount
Implementation | $85k
Pilot included | $25k
Annual operations | $30k
First-year total | $115k
Scenario | Adoption | Time saved | Annual h | Annual capacity | First-year value | Net vs $115k
Downside | 40% | 20% | 864 | $108k | $54k | −$61k
Base | 60% | 30% | 1,944 | $243k | $121.5k | +$6.5k
Upside | 75% | 40% | 3,240 | $405k | $202.5k | +$87.5k
Release the next investment against evidence
Use the full first-year cost, a realistic ramp and explicit go/no-go tests.
BASE-CASE CAPACITY MODEL
INVESTMENT
FIRST-YEAR SENSITIVITY · 50% RAMP
900
×
12 h
×
60%
×
30%
=
1,944 h
Engagements
Research
time
Adoption
Time
saved
1,944 h × $125/h =
$243k
annual capacity equivalent
Remaining implementation
after the pilot $60k.
GO
All four gates hold.
Practice lead owns rollout.
HOLD
Evidence or usage is weak.
Extend within an agreed cap.
STOP
A critical data control fails.
Suspend use and close the issue.
APPROVE $25k NOW
Release the remaining $60k only after the week-12 gate.
Notes: [SlidePoise sources] Generated target visual: /Users/henry/Codes/AI_slide_drafting/output/showcase-revisions/consulting-v3-authoring/slides/s05-investment-decision/work/accepted-slide.png